## Overall Timeline
| 2022 | [78 empty] | 2023
| Oktober | [17 empty] | November | [29 empty] | December | [30 empty] | Januar
| 14.10 | 15.10 | 16.10 | 17.10 | 18.10 | 19.10 | 20.10 | 21.10 | 22.10 | 23.10 | 24.10 | 25.10 | 26.10 | 27.10 | 28.10 | 29.10 | 30.10 | 31.10 | 01.11 | 02.11 | 03.11 | 04.11 | 05.11 | 06.11 | 07.11 | 08.11 | 09.11 | 10.11 | 11.11 | 12.11 | 13.11 | 14.11 | 15.11 | 16.11 | 17.11 | 18.11 | 19.11 | 20.11 | 21.11 | 22.11 | 23.11 | 24.11 | 25.11 | 26.11 | 27.11 | 28.11 | 29.11 | 30.11 | 01.12 | 02.12 | 03.12 | 04.12 | 05.12 | 06.12 | 07.12 | 08.12 | 09.12 | 10.12 | 11.12 | 12.12 | 13.12 | 14.12 | 15.12 | 16.12 | 17.12 | 18.12 | 19.12 | 20.12 | 21.12 | 22.10 | 23.12 | 24.12 | 25.12 | 26.12 | 27.12 | 28.12 | 29.12 | 30.12 | 31.12 | 01.01 | 02.01 | 03.01 | 04.01 | 05.01 | 06.01 | 07.01 | 08.01 | 09.01 | 10.01 | 11.01 | 12.01 | 13.01 | 14.01 | 15.01 | 16.01 | 17.01 | 18.01 | 19.01 | 20.01 | 21.01 | 22.01 | 23.01 | 24.01 | 25.01 | 26.01 | 27.01 | 28.01 | 29.01
T1: Administrative
T1.1 Semester Project Time Schedule
T1.2 Work out Semester Project title and work packages
T1.3 Sign Semester Project Agreement
T1.4 Add Semester Project in mystudies
T1.5 Important Due Dates
T2: Literature Research
T2.1 Literature Research
T2.2 Similar VR R comparison test? What test design did they use?
T2.3 Limiting FoV in RL
T2.4 FoV, for what is it important? What are effects of limited FoV?
T2.5 What movement data did other papers capture with VR RL comparisons?
T3: User Study Design
T3.1 Study Design First Draft
T3.2 Test Protocol
T3.3 Get aquainted with Unity
T3.4 Get aquainted with other programs
T3.5 Virtual Reality Test Design
T3.6 Reality Test Design
T3.7 Data capture VR vs. Reality
T3.8 Test and validate the study design
T4: User Study at ETH
T4.1 Send out invitation and set up study test days
T4.2 User testing
T5: Evaluation of Results and Documentation
T5.1 Data evaluation
T5.2 Mid-term Presentation
T5.3 Actually writing the report
T5.4 Giving to people to read and get feedback
T5.5 Rework and correct text and passages
T5.6 Detail Work and other small stuff
T5.7 Thesis Presentation