## Quartalsplan
| Work packages |  | October |  |  | November |  |  |  |  | December |  |  |  | January
|  |  | KW 41 | KW 42 | KW 43 | KW 44 | KW 45 | KW 46 | KW 47 | KW 48 | KW 49 | KW 50 | KW 51 | KW 52 | KW 1 | KW 2 | KW 3 | KW 4
Administrative | 1.1 | Time schedule | bar: October KW 41 to October KW 42
| 1.2 | Title and work packages | bar: October KW 41 to October KW 43
| 1.3 | Sign administrative documents | bar: October KW 41 to October KW 43
| 1.4 | Mystudies | bar: October KW 41 to November KW 44
| 1.5 | Set important due dates
Literature Review | 2.1 | Literature Research | bar: October KW 41 to November KW 45
| 2.2 | Similar VR R comparison test? What test design did they use? | bar: October KW 41 to October KW 43
| 2.3 | Limiting FoV in RL | bar: October KW 41 to October KW 43
| 2.4 | FoV, for what is it important? What are effects of limited FoV? | bar: October KW 41 to October KW 43
| 2.5 | What movement data did other papers capture with VR RL comparisons? | bar: October KW 41 to October KW 43
User Study Design | 3.1 | Study Design First Draft | bar: October KW 41 to October KW 43
| 3.2 | Test Protocol | bar: October KW 41 to November KW 44
| 3.3 | Get aquainted with Unity | bar: October KW 41 to November KW 45
| 3.4 | Get aquainted with other programs | bar: October KW 41 to November KW 45
| 3.5 | Virtual Reality Test Design | bar: October KW 41 to November KW 48
| 3.6 | Reality Test Design | bar: October KW 41 to November KW 48
| 3.7 | Data capture VR vs. Reality | bar: October KW 41 to November KW 48
| 3.8 | Test and validate the study design | bar: October KW 41 to November KW 48
User Study | 4.1 | Send out invitation to User Study | bar: November KW 47
| 4.2 | User Study | bar: November KW 47 to December KW 51
Evaluation, Presentation and Documentation | 5.1 | Data evaluation | bar: November KW 47 to December KW 52
| 5.2 | Mid-term Presentation | bar: November KW 47
| 5.3 | Actually writing the report | bar: November KW 47 to December KW 52
| 5.4 | Giving to people to read and get feedback | bar: December KW 51 to January KW 1
| 5.5 | Rework and correct text and passages | bar: December KW 51 to January KW 2
| 5.6 | Detail Work and other small stuff | bar: December KW 51 to January KW 2
| 5.7 | Thesis Presentation | bar: January KW 2

## Workpackages
| Work packages |  | Objectives/Results | Approach
Administrative | 1.1 | Time schedule | Overal time schedule | Just write it down, rework with tutor if necessary
| 1.2 | Title and work packages | Think about the title and if it is fitting for the work | After thinking about study design, reconsider the title if it is still fitting
| 1.3 | Sign administrative documents | Have the documents signed | Take a pen, sign the document
| 1.4 | Mystudies | Added project to mystudies | Go on mystudies, add the project
| 1.5 | Set important due dates | Based on time schedule, start fixing important due dates
Literature Review | 2.1 | Literature Research | Find fitting literature, try and understand the field and what approaches techniques were used in the past, what worked? | Google Scholar and other publishing sites
| 2.2 | Similar VR R comparison test? What test design did they use? | Are there any papers on similar VR E comparison tests?
| 2.3 | Limiting FoV in RL | How did the other papers limit FoV in R?
| 2.4 | FoV, for what is it important? What are effects of limited FoV? | Effects of FoV in general?
| 2.5 | What movement data did other papers capture with VR RL comparisons? | How did they capture and evaluate data in other papers?
User Study Design | 3.1 | Study Design First Draft | Have a first idea on how the used study could look like | Use the literature found for inspiration and use elements that seem to have worked well
| 3.2 | Test Protocol | Come up with a test protocol(s) for the user study | Write and think about what approach and which order is the most useful
| 3.3 | Get aquainted with Unity | Get to know unity | Use the suggested tutorial as well as many youtube videos.
| 3.4 | Get aquainted with other programs | Learn to use any additional necessary programs | Learning by doing
| 3.5 | Virtual Reality Test Design | Come up with the test design in VR | Use unity, maybe Blender to come up with the VR test grounds
| 3.6 | Reality Test Design | Come up with the test design in Reality | Plan and build necessary devices
| 3.7 | Data capture VR vs. Reality | How to data capture in VR and Reality | What data is captured, is it the same, how is it comaprable, get used to work with the capture device for reality
| 3.8 | Test and validate the study design | Combine the different testing grounds and validate the study design | Test test test test, especially test it in the location of A floor
User Study | 4.1 | Send out invitation to User Study | Invite users to the study | Use whatsapp groups, hang flyers, recruit my exercise groups
| 4.2 | User Study | Do the study | Use A Floor to do the tests
Evaluation, Presentation and Documentation | 5.1 | Data evaluation | Evaluate the gained data | Use Rstudio or matlab to work with the data and build the fancy graphs and such to find conclusions
| 5.2 | Mid-term Presentation | Present the study design for final input by the lab | use Powerpoint and present things to the ICVR group
| 5.3 | Actually writing the report | End up with a great report | Use overleaf: Keep calm and keep writing.
| 5.4 | Giving to people to read and get feedback | Getting external feedback from friends and family | Give to Leon, Cecily and others
| 5.5 | Rework and correct text and passages | Improve the report based on feedback | Use the feedback gained by the reviews to improve the report
| 5.6 | Detail Work and other small stuff | Add any more final touches | Check all the figures and tables, are they all the same?
| 5.7 | Thesis Presentation | Final presentation | It's the final countdown presentation!