## Slide 1: Semester Project Weekly Meeting – 15-11-2022
Nicolas Y.C. Triebold

## Slide 2: Last Week
Worked on User Study concept, only some last questions open
Worked on mid-term presentation
Data Logger implementation in unity
Started working on unity scene
Finally feel like I had the time to properly get into the topic and concentrate on working on the semester thesis

## Slide 3: Current Challenges
Data Logger Unity
User study:
  Test Chamber setup and layout
    Idea: Use those poster walls from ETH to create a square room. The could then be removed after every user study to not stand in the way of the corridor.
  Posters with Numbers/Letters or images/symbols? How many?
  Formulating Hypotheses
Mid-term presentation
  Should I present the user study how I think it is best and also reason why I think that way or should I say when I think there are several ways to do something and present all of them and ask for their opinion?

## Slide 4: Next Week
Finish midterm presentation (Goal to finish tomorrow)
Real Life Field of View restriction device
Work on Unity Scene and implement VR :D
  Question: How does it look re PC at LEE on Mo and Tu?