## Slide 1: Semester Project Weekly Meeting – 06-12-2022
Nicolas Y.C. Triebold

## Slide 2: Last Week
Concept user study
  Test proceedures
  Invitation Flyer
  Confirmation E-Mail template
  Study Consent Form
  Completed the Google forms questionnaire (made a second google doc, one for each study order (VR – Reality and Reality – VR), should be shared with you already.
Did a short pilot test with some people from ICVR group
  They automatically focused on the middle of the card when wearing the HMD
  Not much done in with eye movement, this might be different in reality or reality with restricted FoV (!)
Worked on Unity User study implementation
Printed v2 of FoV restriction device
Read Papers and trying to get in to Bayesian Analysis

## Slide 3: User Study Design
User Study at CLA A floor
  Design of gaze focus object: A4 with Letter-Number
  Fixed CLA A floor light and organised partition walls
Three phases:
1. Environment familiarization phase
  Familiarize with environment and FoV restrictions, no measurements
2. Guided Task
  Check trajectrories, speed, TimeToTarget etc. Stopwatch & recording
3. Waiting phase: Let users look around while they have to wait a few min
  Measure curiosity: Check data such as speed, acceleration, deceleration, frequency etc.
Questionnaires

## Slide 4: Current Challenges
Validate v2 FoV restriction device
Unity User Study implementation
  Recording of VIVE Tracker with provided tracking script
  Eye gaze tracking implementation (test needed)

## Slide 5: Next Week
Implement VIVE Tracker Tracking
Test eye gaze tracking (Thu & Fri)
Validate v2 FoV restriction device
Test run for user study