## Slide 1: Semester Project Weekly Meeting – 10-01-2023
Nicolas Y.C. Triebold

## Slide 2: Last Weeks
Finished User Study:
  31 Participants, 13F, 18M, 24.5Y
  1 non-student, 28 BSc/MSc students, 2 PhDs students
  28 applied sciences, 1 natural, 1 social, 1 humanities
Data Tidying and Analysis
Data Visualisation
Report Writing
Final presentation preparation

## Slide 3: Current Challenges
Data Tidying and Analysis
Data is very very messy and heavily user independant.
Had to label 93 data sheets with 10’000 up to 25’000 lines of code
  Most of which I had to label by hand, taking from 30 minutes to over an hour per data sheet…
1800 lines of code just to tidy and transform the data…

## Slide 4: Next Week
Finish labeling the last data sets
Data visualization
Final presentation preparation